## Construction Programme
ABC Construction Ltd
Project: Office Fitout
Generated: 25/03/2026
ID | Activity Description | Start | End | Dur. | Deps | Notes | Responsible
1 | PRELIMINARIES |  |  |  |  | SECTION HEADER
1.1 | Site establishment | 13-Jan-26 | 14-Jan-26 | 2d |  |  | MC
1.2 | Material delivery | 15/01/2026 | 15/01/2026 | 1 | 1.1 |  | Subbie
2 | FRAMING WORKS |  |  |  |  | SECTION HEADER
2.1 | Wall framing - Level 1 | 2026-01-16 | 2026-01-20 | 5 | 1.2 |  | Internal
2.2 | Wall framing - Level 2 | Jan 21, 2026 | Jan 25, 2026 | 5 | 2.1 | Depends on 2.1 | Internal
2.3 | Ceiling framing | 26/01/26 | 30/01/26 |  | 2.2 |  | Internal
3 | LININGS |  |  |  |  | SECTION HEADER
3.1 | Gib fixing - walls | 31-Jan-2026 | 06-Feb-2026 | 5 days | 2.1,2.2 | Multiple deps | Internal
3.2 | Gib fixing - ceilings | 07/02/2026 | 12/02/2026 | 4 | 3.1,2.3 |  | Internal
3.1 | Gib fixing - walls | 31-Jan-2026 | 06-Feb-2026 | 5 days | 2.1,2.2 | DUPLICATE | Internal
4 | STOPPING & FINISHING
4.1 | Stopping coat 1 | 13/02/2026 | 17/02/2026 | 3 | 3.1 |  | Subbies
4.2 | Stopping coat 2 | 18/02/2026 | 20/02/2026 | 2 | 4.1 |  | Subbies
4.3 | Final stopping | 21/02/2026 | 25/02/2026 |  | UNKNOWN |  | Subbies